## Slide 1: ABS Cultural and Ethnic Review Timeline
Apr May Jun Jul Aug Sept Oct Nov Dec
2025
Public
Consultation
Round 1
Submissions accepted through
ABS Consultation Hub Early April - 16 May 2025
Post-consultation engagement
Follow up with stakeholders
(if required)
Proposed release of updated ASCCEG* November
2025
Drafting changes to ASCCEG
Based on submissions and research
May - July 2025
Public
Consultation
Round 2
Submissions accepted through
ABS Consultation Hub
Planned to start mid July 2025
(for 6 weeks)*
Post-consultation engagement and final changes
Share outcome of public consultation and finalisation of publication
October 2025
Share outcome of public consultation
* The start and end dates of public consultation (round 2) and release date for ASCCEG will be confirmed later in 2025.